## Fee Proposals
Fee Proposals
Received | Tender Number | Erf Number | Suburb | Client | Project Type | Category | Sent | Follow Up | Notes | Column1 | Status | Accepted | Rejected | Reason | Value | sent data | accepted data | rejected data
06/05/2021 | T017 | Erf 958 | Jeffreys Bay | Mrs G. Fugard | Add & Alt | Residential |  |  | needs 6 months before follow up | Project Started | Project Started |  |  |  | 6000 | TRUE | TRUE | FALSE
22/01/2024 | T161 | PTN 1 / 658 | Kirkwood | Paul Slabbert - Unifruitti | Add & Alt | Industrial |  |  | Exporting in process | Project Started | Project Started |  |  |  | 38000 | TRUE | TRUE | FALSE
| T168 | Erf 600 | Summerstrand | Mr Shmidt | Add & Alt | Residential |  |  | Bayside Guest House | Follow Up | Land Surveyor & RoR / Revise FP |  |  |  | 0 | FALSE | FALSE | FALSE
| T176 | Erf 758 | Summerstrand | Yusuf Cassim | Add & Alt | Residential |  |  | Student Accommodation | Follow Up | As-Built |  |  |  | 0 | FALSE | FALSE | FALSE
| T183 | Erf 184 | Royalston | Shaun & Leigh-Anne de Villiers | Add | Residential |  |  | Looking for contractor | Follow Up | On Hold - Follow Up |  |  |  | 0 | FALSE | FALSE | FALSE
| T191 | Erf 730 | Theescombe | Arnold and Bianca Avanant | Add & Alt | Residential |  |  | Revise SDP for TP Application | Follow Up | Make appointment for site visit |  |  |  | 0 | FALSE | FALSE | FALSE | Diane
| T192 | Erf 731 | Theescombe | Arnold and Bianca Avanant | Add & Alt | Residential |  |  | Revise SDP for TP Application | Follow Up | Make appointment for site visit |  |  |  | 0 | FALSE | FALSE | FALSE | Diane
| T197 | Erf 660 | Theescombe | Francois de Klerk | New Design | Residential |  |  | Offer void | Cancelled | Cancelled |  |  |  |  | FALSE | FALSE | FALSE
| T200 | Erf 781 & 814 | Redhouse | Paul Moorcraft - Stormberg Foods | Add & Alt | Industrial |  |  | Drawings sent as requested | Follow Up | Silence |  |  |  | 0 | FALSE | FALSE | FALSE
| T203 | Erf 81 | Newton Park | Rochlè Bloem | Add & Alt | Residential |  |  | TP issues | Follow Up | make decision |  |  |  | 35650 | FALSE | FALSE | FALSE
| T210 | Erf 2901 | Sea Vista | John Henrik | New Design | Industrial |  |  | Update on tender list | On Hold | Waitning on Client |  |  |  | 57250 | TRUE | FALSE | FALSE
| T214 | Erf 1196 | Newton Park | Martin PSG | Add & Alt | Commercial |  |  |  | Follow Up | Follow up with client |  |  |  | 92472 | TRUE | FALSE | FALSE
| T218 | Erf 277 | Royalston | J.G & Denise Le Roux | New Design | Residential |  |  |  | Project Started | Project started |  |  |  | 125650 | TRUE | TRUE | FALSE
| T219 | Erf 3304 & 2498 | Humansdorp | Sanjay | Add & Alt | Commercial |  |  | Client to consolidate | Follow Up | Waitning on Client - Talk to Andries |  |  |  | 0 | FALSE | FALSE | FALSE
| T220 | Erf 5565 | St Georges | Rose - Fernkloof | Add & Alt | Residential |  |  | Rose to send through fire report | Urgent Quote | On Hold |  |  |  | 0 | FALSE | FALSE | FALSE
| T221 | Erf 6181 | Kabeljous | Wimpie Coetzee | Add & Alt | Residential |  |  | Waiting for client documentation | On Hold | On Hold |  |  |  | 0 | FALSE | FALSE | FALSE
| T222 | Erf 154 | Royalston | Alonge & Alfred Ntintili | Add & Alt | Residential |  |  | Additions to existing | Follow Up | Waiting on Client |  |  |  | 9000 | FALSE | FALSE | FALSE
| T223 | Erf 2063 | Jeffreys Bay | Annette Lindeque | Add & Alt | Residential |  |  | Joos' project | Project Started | Project started |  |  |  | 14185 | TRUE | TRUE | FALSE
| T224 | Erf 1508 | Newton Park | Johnathan - RECTRON | Add & Alt | Commercial |  |  | Additional fee proposal after site visit | Follow Up | Waiting on Client |  |  |  | 3200 | TRUE | FALSE | FALSE
| T225 | Erf 3040 | Lorraine | Fred Hirst | Add & Alt | Residential |  |  | Shannon to follow up | Follow Up | Waiting on Client |  |  |  | 46470 | TRUE | FALSE | FALSE
| T226 | Erf 2088 | Newton Park | Herman Strydom | Add & Alt | Commercial |  |  | Discuss and send | Project Started | Fee Proposal Complete! |  |  |  | 51050 | TRUE | TRUE | FALSE
| T227 | Erf 397 | Theescombe | Francois De Klerk | New Design | Residential |  |  | Erf 137 development to take preference | On Hold | On Hold |  |  |  | 0 | FALSE | FALSE | FALSE
| T228 | Erf 137 | Lorraine | Francois de Klerk | New Design | Residential |  |  | Stormwater plan from Don | On Hold | Feesability study being conducted |  |  |  | 0 | FALSE | FALSE | FALSE
| T229 | Erf 1202 | Colchester | Fabian | Add & Alt | Residential |  |  |  | Project Started | Project started |  |  |  | 3265 | FALSE | TRUE | FALSE
| T230 | Erf 1612 | Walmer | Donovan Long | Add & Alt | Commercial |  |  | Sent on 11.09.2024 | Follow Up | Follow up with client |  |  |  | 31450 | TRUE | FALSE | FALSE
| T180 | Erf 2170 | Newton Park | Herman Strydom | Add | Residential |  |  | Discuss and send | On Hold | Fee Proposal Complete! |  |  |  | 128465 | TRUE | FALSE
| T175 | Erf 1436 | Theescombe | Kelly & Ryan Silbernagel | Add & Alt | Residential |  |  | Land Surveyor needed | Follow Up | Waiting for John's response |  |  |  | 0 | FALSE | FALSE
| T | Erf 6820 | Uitenhage | Stephan Oosthuizen | Add | Industrial |  |  | Transformer Roof included in Eng Fee | Follow Up | Fee Proposal |  |  |  | 4500 | TRUE | FALSE | FALSE
| T | Erf 963 | Mill Park | Mr Shmidt | Add & Alt | Commercial |  |  |  | Follow Up | Awaiting TP Info |  |  |  | 0 | TRUE | TRUE
| T | Erf 93 | Newton Park | Herman Strydom | As Built |  |  |  |  | On Hold |  |  |  |  | 0 | FALSE | FALSE
| T233 | Erf 232 | Royalston | Corne Rossouw | Add | Residential |  |  | Quote for additions | Project Started | To be quoted |  |  |  | 16500 | TRUE | TRUE
| T232 | Erf 3554 | Jeffreys Bay | Chrstiaan Venter | Add & Alt | Residential |  |  |  | Follow Up | Quote Sent |  |  |  | 0 | TRUE
| T231 | Erf 29201 | Uitenhage | Riaan Botha | Add | Industrial |  |  | VWSA - Durr | Follow Up | Quote Sent |  |  |  | 42980 | TRUE
| T234 | Erf 980 | Theescombe | Juanita Krauspe | As Built | Residential |  |  | Andries Job | On Hold | Client to deliver plans 09.10.2024 |  |  |  | 30885 | FALSE
| T235 | Erf | Jeffreys Bay | Flip van Zyl | Municipal Research | Residential |  |  |  | Follow Up |  |  |  |  | 685
| T187 | Erf 897 | Paradise beach | Pierre van den Berg | Add & Alt | Residential |  |  |  | Project Started |  |  |  |  | 28250 | TRUE | TRUE
| T201 | Erf 395 | Gamtoos | Dave Orton | Add & Alt | Residential |  |  |  | Project Started |  |  |  |  | 7000 | TRUE | TRUE
| T202 | Erf | Royalston | Dr Manga | New Design | Residential |  |  |  | Follow Up |  |  |  |  | 400000 | TRUE | TRUE
| T204 | Erf 3935 | Sea Vista | John Henrik | New Design | Industrial |  |  |  | Project Started |  |  |  |  | 59500 | TRUE | TRUE | TRUE
| T207 | Erf 406 | Royalston | Hugo Ferreira | New Design | Residential |  |  |  | Project Started |  |  |  |  | 115000 | TRUE | TRUE
| T208 | Erf 3729 | Theescombe | Jennifer & Anzel | New Design | Residential |  |  |  | Follow Up |  |  |  |  | 27500 | TRUE | FALSE
| T209 | Erf 263 | Royalston | Dirkie Fourie | Add & Alt | Residential |  |  |  | Project Started |  |  |  |  | 7050 | TRUE | TRUE
| T211 | PTN 56 of 52 | PTN 56 of 52 | Goedemoeds Fontein | Municipal Research | Residential |  |  |  | Follow Up |  |  |  |  | 9500 | FALSE | FALSE
| T212 | Erf 7B | Royalston | Nkosi Watson | New Design | Residential |  |  |  | Project Started |  |  |  |  | 8640 | TRUE | TRUE
| T213 | Erf 7A | Royalston | Nkosi Watson | New Design | Residential |  |  |  | Project Started |  |  |  |  | 7500 | TRUE | TRUE
| T216 | Erf 5788 | Walmer | Cuan Roberto Lippert | Add & Alt | Residential |  |  |  | Follow Up |  |  |  |  | 9800 | FALSE | FALSE
| T217 | Erf 1062 | Jeffreys Bay | Garth Metrovich | New Design | Residential |  |  |  | Follow Up |  |  |  |  | 107550 | TRUE
| T | [8 empty] | Urgent Quote | [5 empty] | FALSE
1524947
| Quote Totals |  |  |  | Conversion Rate
| Total Items | 47 |  |  | Total | 42
| Items Completed | 26 | 54.17% |  | Accepted | 6
| Items To Do | 21 | 43.75% |  | Rejected | 0
| Theo Koutsidis | Aston Arms Shopping Centre

## Current Projects
Current Projects List
AP Number | Erf Number | Allotment | Name | Project Type | Catagory | Assignee | Start Date | Due Date | Notes | Completed | Project Name
248 | 27 | Kini Bay | Johan Jacobs | Add & Alt | Residential | Shannon |  |  |  |  | AP248 - Erf 27_House Jacobs
260 | 923 | Walmer | Aubrey De Chalin | Add & Alt | Commercial | Shannon |  |  | Crafty Arts |  | AP260 - Erf 923_Crafty Arts
366 | 952 | Westering | Xavier & Nadine May | Add | Residential | Shannon |  |  |  |  | AP366 - Erf 952_House May
368 | 1468 | Jeffreys Bay | Mnr de Beer | Add & Alt | Residential | Joos |  |  |  |  | AP368 - Erf 1468_House de Beer
398 | 2826 | Korsten | Chris Kaladelis | Add & Alt | Commercial | Yendly |  |  |  |  | AP398 - Erf 2826_U-Save
404 | 1784 | Jeffreys Bay | Karen Maritz | Add & Alt | Residential | Shannon |  |  |  |  | AP404 - Erf1784_House Maritz
429 | 263 | Royalston | Dirkie Fourie | Add & Alt | Residential | Ethan |  |  |  |  | AP429 - Erf 263_House Fourie
452 | 425 | Theescombe | Shaun Henderson | Add & Alt | Residential | Ethan |  |  |  |  | AP452 -Erf 425_House Henderson
454 | 2473 | Jeffreys Bay | Jeff Smith | Add & Alt | Residential | Joos |  |  | Follow up with Joos |  | AP454 - Erf 2473_House Smith
456 | 19 | Cotswold | Elizabeth Williams | Add & Alt | Residential | Shannon |  |  |  |  | AP456 - Erf 19_House Williams
471 | 8081 | Jeffreys Bay | Bongi Ncalu | New Design | Residential | Yendly |  |  |  |  | AP471 - Erf 8081_House Ncalu
472 | 8010 | Jeffreys Bay | Bongi Ncalu | New Design | Residential | Ethan |  |  |  |  | AP472 - Erf 8010_House Ncalu
480 | 1278 | Marina Martinique | Dawie van den Heever | New Design | Residential | Yendly |  |  |  |  | AP480 - Erf 1278_House van den Heever
481 | 128 | Summerstrand | Yusuf Cassim | Add & Alt | Residential | Yendly |  |  |  |  | AP481 - Erf 128_Student Accommodation
485 | PTN 58 / PTN 10 | George | Shannon Burger & Gierieke | New Design | Residential | Ethan |  |  |  |  | AP485 - Ptn 58 of Ptn 10_House Burger
488 | 5565 | St Georges | Sheldon Norris | Add & Alt | Residential | Ethan |  |  |  |  | AP488 - 5565_House Norris
500 | 7A | Royalston | Nkosi Watson | New Design | Residential | Yendly |  |  |  |  | AP500 - Erf 7A_Lifestage
500 | 7B | Royalston | Nkosi Watson | New Design | Residential | Yendly |  |  |  |  | AP500 - Erf 7B_Lifestage
501 | 897 | Paradysstrand | Pier van den Berg | Add & Alt | Residential | Joos |  |  |  |  | AP501 - Erf 897_House MacDonald
502 | 1163 | Colchester | Tabisa Mbodamo | Add & Alt | Residential | Ethan |  |  |  |  | AP502 - Erf 1163_House Tabisa
503 | 3935 | Sea Vista, St Francis Bay | John Henrick | New Design | Industrial | Yendly |  |  |  |  | AP503 - Erf 3935_JT Factory
504 | 577 | Plettenberg Bay | Sewes Meiring | Add & Alt | Residential | Ethan |  |  |  |  | AP504 - Erf 577_House Sewes
505 | 395 | Gamtoos Mouth | Dave Orton | Add & Alt | Residential | Yendly |  |  |  |  | AP505 - Erf 395_House Orton
506 | 6820 | Kelvin Steet | Stephan Oosthuizen | Add & Alt | Industrial | Shannon |  |  |  |  | AP506 - Erf 6820_Sovereign Foods
507 | 12082 | Kruisrevier | Stephan Oosthuizen | Add & Alt | Industrial | Shannon |  |  |  |  | AP507 - Erf 12082_Sovereign Foods
509 | 406 | Royalston | Hugo Ferreira | New Design | Residential | Ethan |  |  |  |  | AP509 - Erf 406_House Ferreira
510 | 7/444 | Florence Nature Reserve | Louie Brown | New Design | Residential | Ethan |  |  |  |  | AP510 - Ptn 7 of 444_House Brown
511 | 2063 | Jeffreys Bay | Annette Lindeque | Add & Alt | Residential | Joos |  |  |  |  | AP511 - Erf 2063_House Lindeque
512 | 277 | Royalston | J.G. & Denise Le Roux | New Design | Residential | Shannon |  |  |  |  | AP512 - Erf 277_House Le Roux
513 | 1202 | Colchester | Fabian Robert | Add & Alt | Residential | Yendly |  |  |  |  | AP513 - Erf 1202_House Roberts
514 | 958 | Jeffreys bay | Mrs G. Fugard | Add & Alt | Institutional | Shannon |  |  | 7th Haven |  | AP514 - Erf 958_7th Haven
515 | 963 | Newton Park | Mr Schmidt | Add & Alt | Commercial |  |  |  | RITCO |  | AP515 - Erf 963_RITCO
DP4296 | Ptn 1 / 658 | Kirkwood | Paul Slabbert | Add & Alt | Industrial | Ethan |  |  |  |  | DP4296_Ptn 1 of 658_Uni Fruity
434 | 3935 | Sea Vista, St Francis Bay | John Henrick | New Design | Industrial | Yendly |  |  |  |  | AP434 - Erf 3935_JT Factory[Phase 1]
516 | 2088 | Newton Park | Herman Strydom | As Built | Commercial | Yendly |  |  | TRICO |  | AP516 - Erf 2088_TRICO
517 | 93 | Newton Park | Herman Strydom | Add & Alt | Residential | [5 empty] | AP517 - Erf 93_????
518 | 2170 | Newton Park | Herman Strydom | New Design | Residential | Shannon |  |  | Apartments |  | AP518 - Erf 2170_New Aprtments
LD491 | 564 | Tsitisikamma | Judy Woodgate | Add & Alt | Industrial |  |  |  | Crystal |  | LD491 - Erf 564_Tsitsikamma Crystal
426 | 405 | Westering | Mr. van Vollensteen | Add & Alt | Residential | [5 empty] | AP426 - Erf 405_House van Vollensteen
446 | 158 | Royalston | Pam Mtolo | New Design | Residential | Yendly |  |  |  |  | AP446 - Erf 158_House Mtolo
38
0

## Projects Tracker
Projects Status
Priority | Project Name | Allotment | Assigned to | Brief Summary | Status | Notes | Next Step | Last DATE actioned | Current DATE | Lapsed Days
Low | AP248 - Erf 27_House Jacobs | Kini Bay | Yendly | Building plan has been revised. Had a conversation with Reza concerning the need to apply for an extension of time. He notified that the plan is still open and from previous mails the confirmation of the building not being in construction for a period of time the process is as follows; Followed up with Tracy and Reza regarding the extension of time, unfortunatley the plans has lasped and the client is to pay a fee of half the previous building plan submission fee plus the additional sqm. The Laspe decision has been reversed. Clients plans still Valid | Client coming in on Thursday the 5th of June 2025 | 1. The plan is still open and will remain open until the plan is resubmitted, 2. Building plan approval must indicate the existing in grey and new alterations in red. 3. Check for plan fees as it was completed during the building phase… “Bennie was on site and suggested an amended plan.” – clients words Note: Make sure that the removal of restrictions has been noted and all TPA application have been added to the submission. | Client to sign off the plans and documents. Submit the submission plans to the municiplaity. | 2025-05-28 | 2025-06-02 | 4
Completed | AP260 - Erf 923_Crafty Arts | Walmer | Yendly | Plans are being walked for SDP submission, Town Planner has accepted the parking requirements and all proposed internal changes for Art Gallery. The SDP is being walked and the challenge now lies with Transport and Environmental sign off on the walking sheet. The plan has been altered, amended and approved by Aubrey. The existing must be indicated as grey the proposed as red. THIS WILL BE A NEW APPLICATION. | Plans submitted 29/04/2025. Plans have been deferred. Plans have been resubmitted on the 21st May 2025. Awaiting TDL application | Roads and storm water requested another storm water channel. Another meeting will be held with Shannon Adams on Friday (28/02/2025). Following the meeting the plans should be finalized and submitted fo rMunicipal submission. Note: Sewer Levy, TDL payment needs to be paid before municipal submission can take place.24/04/25-Submitted | Waiting for Transportation and Planning to provide feedback on the TDL fee. Waiting for results of the Resubmission | 2025-05-20 | 2025-06-02 | 10
Medium | AP366 - Erf 952_House May | Westering | Ethan | The Attorneys are currently checking their books for oustanding fees as agreed in the fee proposal. Kindly see if Noeksie has repsonded from DTS law as she is the person assisgned to the project. | The site plan is complete, however the elevation and sections o fth eproperty still needs to be submitted. See the Statement for details on what has been paid by the Attorneys as they have kept monies aside for the job. | Follow up with Attorney for the outstanding payment and available funds on the property. | G2 to Gazette Application Applications opn 6 Jan 2025 Owners to endorce Title Deed_ Submit Municipal Drawings after the Title deed has bee endorsed. | 2025-04-29 | 2025-06-02 | 25 | Tertius - email lawyers Sections & Elevations
Completed | AP368 - Erf 1468_House de Beer | Jeffreys Bay | Joos | Note: Comply with fire and NBR for Part S. | Plans submitted to council | at council for two months to date 25,09,2024 | Awaiting Approval. | 0 | 0 | 0
High | AP398 - Erf 2826_U-Save | Korsten | Yendly | Additions and Alterations to existing burnt down building | Waiting for In Lieu fee from Zama as SOP has not been finalized. | Municipality clueless | Chat with Maartjie on what we can do. Still waiting confirm S.O.P | 2025-02-26 | 2025-06-02 | 69 | Tertius - Follow up with Director and CM Find out about falidity period of RoR
High | AP404 - Erf1784_House Maritz | Jeffreys Bay | Yendly | Departure of height restrictions. Owner has been contected on the 25/02/2025 and she will make the Architectural Payment for the project and confirm the correctness for the plans. A quotation for the Ovvio submission has been prepared and is on file, alternatively there is one that has been sent to the client Karin Maritz. | Waiting for the client to confirm the submission and to sign off the building plans. | Submit Municipal Building plans on payment of Invoice and approval of Building Plans. Please do not forget to update the new roof and indicate the new height line. | Follow up with Client on payment on engineering fees. | 2025-05-27 | 2025-06-02 | 5 | Tertius - appoint engineers
Completed | AP429 - Erf 263_House Fourie | Royalston | Ethan | New residential design originally with ammendments to the plans. | APPROVED | APPROVED | APPROVED | 0 | 0 | 0
Completed | AP452 -Erf 425_House Henderson | Theescombe | Ethan | Proposed Alterations to existing previously approved building | Municipal Submission Done | APPROVED | APPROVED | 1899-12-31 | 1899-12-31 | 0 | New Year
Completed | AP454 - Erf 2473_House Smith | Jeffreys Bay | Joos | Removal of Building line restrictions has been removed and has been indicated on site as such. Joos to resubmit the building plans on Ovvio | Building plans resubmission | Follow up with Joos on progress | Waiting on KOUGA | 0 | 0 | 0 | Assessment - call KOUGA to follow up.
High | AP456 - Erf 19_House Williams | Cotswold | Ethan | Additions and alterations to existing building to be completed, check and verified fo raccuracy. | Title Deed to be endorsed and plans to be resubmitted. Follow up with client. | Owner to endorse Title Deed for the approved removal of restrictions Followed up - no answer | Endorsement in process - Follow up with Client | 2025-05-27 | 2025-06-02 | 5 | Check date of RoR with Maartje Tertius - Email DTS regarding endorsement | email sent
Low | AP471 - Erf 8081_House Ncalu | Jeffreys Bay | Yendly | New Residential Design | Stage 3 Complete | Project on hold because owner has other priorities | Continue and completed until Stage 4.1 Follow up on the way forward | 2025-02-26 | 2025-06-02 | 69 | Tertius - Follow up
Low | AP472 - Erf 8010_House Ncalu | Jeffreys Bay | Ethan | New Residential Design | Stage 3 Complete | Project on hold because owner has insufficient funds | Continue and completed until Stage 4.1 Follow up on the way forward | 2025-02-26 | 2025-06-02 | 69 | Tertius - Follow up
Completed | AP480 - Erf 1278_House van den Heever | Marina Martinique | Yendly | New residential design | APPROVED | APPROVED | APPROVED | 0 | 0 | 0
High | AP481 - Erf 128_Student Accommodation | Summerstrand | Yendly/Ethan | Building Plans has been updated and ready for resubmission for the application. The Title Deed must be updated as per the Gazette. | Maartjie Gazetted application | Maartjie to redo application for student accomodation. All plans have been drafted acordingly. Update with client regularly for the endorsed Title Deed. | We have sent Maartje the updated as-built as per her request to do her application.Yusuf to endorse title deed | 2025-05-19 | 2025-06-02 | 11
Low | AP485 - Ptn 58 of Ptn 10_House Burger | George | Ethan | New residential design | Appointed new town planner | * subdivision needed on agricultural land - because max dwelling units had been achieved | Look at payments breakdown from Andries. | 2024-09-25 | 2025-06-02 | 176
High | AP501 - Erf 897_House MacDonald | Paradysstrand | Joos | Additions & Alterations to existing dwelling | Submission Documentation | Clients aprroved proposals | Preparing Submission drawings_ No contact from client has been received. | 2025-02-26 | 2025-06-02 | 69 | Check status
Low | AP502 - Erf 1163_House Tabisa | Colchester | Ethan | Partial redesign and submission of building plans | Plans completed | * Land Survey received | Waiting for client and final invoice outstanding from G2. | 2025-02-26 | 2025-06-02 | 69 | Tertius
High | AP503 - Erf 3935_JT Factory | Sea Vista, St Francis Bay | Yendly | Design of new Factory has been approved by client. New plans processing on Ovvio under Land Use Applications (Diane Ovvio). | SDP Submitted - 5 Dec. | contact Chuma or Tabelo on process of SDP and on further steps. | Follow up after 30 days completed. SDP submission completed. Payment of sewer levy and Transport levy to be paid and attached to Municipal Submission. Remember that only a Residential dwelling signs in as a sub economic dwelling. Currently getting documents for tempory occupation. | 2025-05-29 | 2025-06-02 | 3 | Confirm with Kevin and Grant (Contractors) for the McCleods Invoice that must be paid fo rfire safety sign off on old plan
Low | AP504 - Erf 577_House Sewes | Plettenberg Bay | Ethan | Additions to existing dwelling | * Construction in progress * Continuous additions added with plans being updated as built progresses | On hold | Waiting on Andries | 2024-10-28 | 2025-06-02 | 153 | Follow up with Andries
Completed | AP505 - Erf 395_House Orton | Gamtoos Mouth | Yendly | Revise existing plans | Submitted |  | Paid in full | 0 | 0 | 0
High | AP506 - Erf 6820_Sovereign Foods | Kelvin Steet | Yendly | Additions and alterations to existing building and the addition of Solar Panels | Proposed drawings send for client approval (Full SDP set) | Sent proposed parking to all relevant parties - Awaiting feedback/go-ahead. SDP is ready for submission Site Visit to update SDP. 26/02/2025_ Drawing being updated according to what is on site. Including the proposal to have more parkign bays as the not-in-use structures have been fixed and are currently beng used as storage and office space. | Awaiting Approval from client as well as payment for the SDP submission fee.. | 2025-05-21 | 2025-06-02 | 9 | Tertius
High | AP507 - Erf 12082_Sovereign Foods | Kruisrevier | Yendly | Additions of a water treatment plant. And update of SDP | TIA has been submitted | SITE PLAN UPDATED - ADDITIONAL BUILDINGS | TIA has been submitted. Follow up with Shaun Abrahams on the acceptance and letter for the approved TIA. | 2025-05-21 | 2025-06-02 | 9 | Tertius
Completed | AP509 - Erf 406_House Ferreira | Royalston | Ethan | Design of a new 4 bedroom dwelling on Erf 406, Royalston | * Design finalised with client approval. * Preparing Submission Drawings | Include roof areas and a door and window schedule for costing drawings | Plans ready for submission - waiting on client's go-ahead | 0 | 0 | 0
Completed | AP510 - Ptn 7 of 444_House Brown | Florence Nature Reserve | Ethan | New dwelling using timber construction, cladded with half logs. | APPROVED | APPROVED | APPROVED | 0 | 0 | 0
Completed | AP511 - Erf 2063_House Lindeque | Jeffreys Bay | Joos | Addtions and Alterations to existing dwelling | Plans ready for submission | Client is currently overseas Possible ammendments due to something about balustrades | Plans Approved | 0 | 0 | 0
High | AP512 - Erf 277_House Le Roux | Royalston | Ethan | New residential design | APPROVED | Construction in progress. | Meeting to be held 13.12.2024_ Meeting held and client has chosen contractor. Construction in progress | 2025-05-19 | 2025-06-02 | 11
Completed | AP513 - Erf 1202_House Roberts | Colchester | Yendly | Additions and alterations | existing layout issues | Plans to Stage 3 - no submission | Paid in full | 0 | 0 | 0
Low | AP514 - Erf 958_7th Haven | Jeffreys bay | Joos | Additions & Alterations to existing Site | revised plans sent to Maartje | follow up on 30 DAYS Municipal fees outstanding | follow up with maarjie | 2025-02-04 | 2025-06-02 | 85
High | AP515 - Erf 963_RITCO | Newton Park | Ethan | This is to confirm that rezoning in term of the new land use scheme has being an approved although the SDP was not submitted the Transport Development Levy was payed (this can only be verified if a Proof of payment can be located) and ERF Business 3 on ERF 963, Mill Park. The current zoning will only allow the primary use of Offices, Medical Use, Wellness Centre and no processing or workshop will be allowed on-site. The following process will be applicable to the ERF 963 Mill Park; 1. Land Surveyor: (Request see the fee proposal attached) R14 500.00 subject to increase The positions of all existing structures on site is required to be surveyed in order to assist the Town planner in removing the building lines that the altered structures are encroaching. (The previously approved structures are previously approved however, the use of these structures are being changed from filing and storage to processing and jewellery store.) 2. Town Planner: (Please see the fee proposal attached) R33 771.00 subject to increase Due to the zoning which is not finalized as there was no Transport Development Levy payed and The following will need to be addressed in order to assist in the sale of the property and compliance of the illegal use on the property; 2.1 Building line departure (applies to the rear and side boundaries of the previously approved building); 2.2 Parking bay departure (TPA conditions on the quantity of leasable area of the ERF); 2.3 Special consent for the jewellery manufacturing (Business 3 does not allow for manufacturing or a workshop on the property, therefore a special consent application is required to be completed by a registered Town Planner). 3. Site Development Plan submission: (Municipal Submission Fee is R2 207.00) This is required to be completed for all Business zoned erven. This is to ensure that all businesses conform to the Land Use scheme with regards to Health and Safety for personnel working, visiting and passing by the ERF. 4. Heritage Application: (Request has been made for the application fee proposal) R2 000.00 subject to increase The Heritage application is a requirement as the building is a registered Heritage landmark in Gqeberha, therefore any addition on the site may take away the aesthetics of the heritage building in its entirety. 5. Municipal Submission: (Paid for in previous quotation) R 15 000.00 subject to change This submission may only take place once the Registered Town Planner has completed their application and the submitted SDP has been ‘walked’ and approved by all Municipal department officials. All conditions of the SDP must been met and all payments must be paid before the Municipal submission; ie TDL and Sewer Development Levy. Municipal submission fees will need to be paid for the additions made on site. 6. Occupation Certificate: Architectural fee for the collection of COCs; R 5 000.00 subject to increase • COC for electrical installation; • COC for fire safety; • COC for plumbing (may not be applicable as there is no drainage being affected); • COC for glazing installation of the additional doors and windows on the front of the addition; • Engineer’s Form 4. This process is a requirement and cannot be altered or expedited. | Waiting on Maartje for her application. | * Special Consent * parking removal | Fee proposal for entire project[sdp & ms]. Maartje has been paid to continue with her application. Fees has been accepted. | 2025-04-23 | 2025-06-02 | 29
Low | DP4296_Ptn 1 of 658_Uni Fruity | Kirkwood | Ethan | Addtions and Alterations to existing factory. | Waiting on client to restart the project. |  | On Hold | 2024-07-24 | 2025-06-02 | 219
Completed | AP434 - Erf 3935_JT Factory[Phase 1] | Sea Vista, St Francis Bay | Yendly | Design of new Factory | APPROVED | APPROVED | APPROVED | 0 | 0 | 0
High | AP516 - Erf 2088_TRICO | Newton Park | Yendly | As Built drawings have been completed and all proposed drawings have been completed. The proposedamending of all buidling lines must be completed. The submission must be accompanied by the Fairview Urban development approval. All SDP submissions must be completed and kindly note that there is | record plans ready for submission maarjie to do relaxation submit sdp | Awaiting Maartjes application to be complete for the removal of Building lines. | SUBMIT RECORD PLANS 07.02.25. Deferred because SDP was required. | 2025-02-04 | 2025-06-02 | 85 | New ownership - Maartje
Low | AP517 - Erf 93_???? | Newton Park | 0 |  | commence after Erf 2170 |  |  | 2024-12-09 | 2025-06-02 | 123
Low | AP518 - Erf 2170_New Aprtments | Newton Park | Yendly | Design of apartment block, 16 units consisting of 8 x 2 bedroom units and 8 x 1 bedroom units. | commence after Erf 2088 | Maartjie to assist with a TPA for the property. John is currently surveying the site | Finalize the design of the apartments so that we can do a dry run. Waiting for survey from John | 2025-05-20 | 2025-06-02 | 10
Low | LD491 - Erf 564_Tsitsikamma Crystal | Tsitisikamma | 0 | Additions & Alterations | Diane to handle administrative tasks | documents given to clients as requested | waiting on outcome from clients | 2024-12-09 | 2025-06-02 | 123
Low | AP426 - Erf 405_House van Vollensteen | Westering | 0 | Additions & Alterations | Waiting for revised bond holders consent | waiting for bond holders' concent | Departure LUS building line | 2024-12-12 | 2025-06-02 | 120 | Tertius - Follow Up with Maartje
Low | APO500-ERF 6 Unit A | Royalston | Ethan | Proposed dwelling | Plans were submitted 08/05/25 - Plans deferred | Unit A was resubmitted. | Comments signed off | 2025-05-26 | 2025-06-02 | 6
Low | APO500-ERF 6 Unit B | Royalston | Ethan | Proposed dwelling | Plans were submitted 08/05/25 - Plans deferred | Unit B to be submitted once Unit A has been approved. | Aquire and ammend the comments | 2025-05-23 | 2025-06-02 | 7
Low | APO291-ERF 103 Diaz views | Jeffreys Bay | Ethan | Need to resubmit drawings on ovvio and get a submission fee wihich must be sent to the client. | Plans submitted to HOA for approval. HOA has approved the plans. Building plans have been submitted on oovio, waiting KLM receipt. | Resubmit the previous plans that was approved with balustrade. Reason for resubmitting is because the plans lapsed and client did not occupation. | Upload proof of payment to the ovvio system. KLM | 2025-05-28 | 2025-06-02 | 4
Low | APO500 - ERF73 unit B | Royalston | Ethan | Plans have been approved. Plans are to be revised t reflect changes that are on site. | Plans have been revised. | Plans to be reviewed and approved. | Resubmit | 2025-05-23 | 2025-06-02 | 7
Low | ERF 997 | Paradise Beach | Ethan | Joint venture | Plans have submitted on ovvio awaiting klm receipt | Plans have submitted on ovvio awaiting klm receipt | Submit klm reciept | 2025-05-28 | 2025-06-02 | 4
High | 11
Medium | 1
Low | 17
29
Formulas:
Lapsed Days = NETWORKDAYS(Project_Status6[[#This Row],[Last DATE actioned]],Project_Status6[[#This Row],[Current DATE]],Table39[Public Holidays 2024])

## Projects Completed
Projects Completed
Priority | Project Name | Allotment | Assigned to | Brief Summary | Status | Notes | Next Step | Last DATE actioned | Current DATE | Lapsed Days
| AP488 - 5565_House Norris | St Georges | Ethan | Alterations to existing Penthouse appartment | Plans Approved | *Fire plans required for entire appartment building | APPROVED / FINISHED | 2024-11-15 | 2024-12-15 | 21
| AP500 - Erf 7A_Lifestage | Royalston | Yendly | New Dwelling Unit | * Submitted plans on 28.08.2024 * Plan feedback on 13.09.2024 | None | APPROVED / FINISHED | 0 | 0 | 0
| AP500 - Erf 7B_Lifestage | Royalston | Yendly | New Dwelling Unit | * Submitted plans on 28.08.2024 * Plan feedback on 13.09.2025 | None | APPROVED / FINISHED | 0 | 0 | 0
0 | 263 | Residential | Revise existing plans | Submitted |  | Paid in full | 0 | 0 | 0 | 0
0 | 425 | Residential | Additions and alterations | existing layout issues | Plans to Stage 3 - no submission | Paid in full | 0 | 0 | 0 | 0
Medium | AP404 - Erf1784_House Maritz | Jeffreys Bay | Shannon | Second dwelling Application | Plans submitted to counsil | at council for two months to date 25,09,2024 | Awaiting Approval. | 0 | 0 | 0
Medium | AP456 - Erf 19_House Williams | Cotswold | Shannon | Addtions and Alterations to existing dwelling | Plans ready for submission | Client is currently overseas Possible ammendments due to something about balustrades | Plans Approved | 0 | 0 | 0
Medium | AP452 -Erf 425_House Henderson | Theescombe | Ethan | New residential design originally with ammendments to the plans. | APPROVED | APPROVED | APPROVED | 0 | 0 | 0
High | AP454 - Erf 2473_House Smith | Jeffreys Bay | Joos | New residential design | APPROVED | APPROVED | APPROVED | 0 | 0 | 0
Formulas:
Lapsed Days = NETWORKDAYS(Project_Status68[[#This Row],[Last DATE actioned]],Project_Status68[[#This Row],[Current DATE]],Table39[Public Holidays 2024])

## Outstanding Fees
AP NO | CLIENT DETAILS | ERF NO | JOB VALUE | PAY DATE | INV | ACCEPT PAID | PAY DATE2 | INV3 | PROGRESS PAID | PAY DATE4 | INV5 | PROGRESS PAID6 | PAY DATE7 | INV8 | FINAL PAID | ADDITIONAL | INV9 | OUTSTANDING | Column1 | Column2 | Column3
456 | MS E WILLIAMS | 19 | 78477.5 | 2023-03-02 | 884-23 | 47086.5 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 31391 | TITLE DEED ENDORCEMENT | DOUBLE CHECK
457AJS | ME W GRANT | 506 | 25170 | 2023-06-02 | 886-23 | 12585 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 12585 |  | FOLLOW UP WITH ANDRIES
471 | BONTIBASE PROPRIETARY | 8180 | 28000 | 2023-11-07 | 912-23 | 14000 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 14000 | ON HOLD | FOLLOW UP
472 | BONTIBASE PROPRIETARY | 8010 | 17000 | 2023-11-07 | 913-23 | 8500 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 8500 | ON HOLD | FOLLOW UP
478 | DRIES BRIERS - ZONNENZEE | 46 | 6000 | 14/07/2023 | 922-23 | 3000 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 3000 | NO SDP - CAN NOT FINISH
481 | YUSUF CASSIM | 128 | 61650 | 21/08/2023 | 926-23 | 30825 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 30825 | ONLY ON PLAN SUBMISSION
485 | MR GERIKE BURGER | GEORGE | 235750 | 13/11/2023 | 937-23 | 10036.98 | 2024-07-02 | 943-23 | 54207.37 |  |  | 0 |  |  | 0 | 0 |  | 171505.65
378 | MR.SCHMIT | 600 | 21500 | 0 |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 21500 | SEND A STATEMENT - SECRETARY |  | SET UP MEETING
421 | MR B OPPELT | 74 | 15000 | 2023-11-07 | 921-23 | 7500 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 7500 | INVOICE 31,10,2024
434 | MR G VENTER | 3935 & 2896 | 54000 | 13/11/2023 | 920-23 | 27000 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 27000 | INVOICE ON APPROVAL - CHECK AMMENDMENTS
404 | MR K MARITZ | 1784 | 9500 | [5 empty] | 0 |  |  | 0 |  |  | 0 | 0 |  | 9500 | CHECK FILE - PAYMENTS NOT RECORDED
446 | PAM MTOLO (ADDITIONS) | 158 | 11765 | 16/10/2024 | 965-24 | 5882.5 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 5882.5
452 | MR & MRS HENDERSON | 425 | 8500 | [5 empty] | 0 |  |  | 0 |  |  | 0 | 0 |  | 8500 | CHECK FILE - INVOICE DEPOSIT
518 | HERMAN STRYDOM | 2170 | 134465 | [5 empty] | 0 |  |  | 0 |  |  | 0 | 0 |  | 134465
519 | CORNE ROSSOUW | 232 | 16500 | 16/10/2024 | 970-24 | 8250 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 8250 | INVOICE 31,10,2024
516 | HERMAN STRYDOM | 2088 | 51050 |  |  | 25000 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 26050 | CASH DEAL
514 | 7th Haven | 958 | 6000 | [5 empty] | 0 |  |  | 0 |  |  | 0 | 0 |  | 6000 | INVOICE 31,10,2024
512 | J.G. & DENIS LE ROUX | 227 | 125000 | 2024-09-09 | 966-24 | 29527.75 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 95472.25
508 | HENDRICK FOURIE | 263 | 7050 | 25/06/2024 | 959-24 | 3525 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 3525 | INVOICE 31,10,2024 | CHECK INVOICES
509 | HUGO FERREIRA | 406 | 132250 |  |  | 100000 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 32250 | FOLLOW UP
510 | LOUIS BROWN | PTN 18 | 59000 | 2024-04-07 | 960-24 | 29500 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 29500 | INVOICE 31,10,2024
501 | P VAN DEN BERG | 897 | 20000 | 13/09/2024 | 967-24 | 10000 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 10000
502 | TABISA MBODAMO | 1163 | 35293.5 |  |  | 30000 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 5293.5 | INVOICE 31,10,2024
503 | JOHN HENRICKS | PTN 2896 | 64500 | 2024-01-06 | 2312 | 32250 |  |  | 0 |  |  | 0 |  |  | 0 | 0 |  | 32250
|  |  | 1223421 | [14 empty] | 734744.9
[16 empty] | immidiate invoce total |  | 54068.5

## Sheet2
|  |  |  | Projects Tracker | Fee Proposal
Public Holidays 2024 | Project Type | Category | Staff | Priority | Status
2024-01-01 | Add & Alt | Residential | Yendly | High | Project Started
2024-03-21 | Add | Commercial | Ethan | Medium | Follow Up
2024-03-29 | New Design | Industrial | Shannon | Low | On Hold
2024-04-01 | As Built | Health Care | Joos | Completed | Cancelled
2024-04-27 | Municipal Research | Institutional | Tertius |  | Urgent Quote
2024-05-01
2024-05-29
2024-06-16
2024-06-17
2024-08-09
2024-09-24
2024-12-16
2024-12-25
2024-12-26