## Sheet1
| GUBB & INGGS | DATE REQUIRED | DATE RECEIVED
Information Required Schedule
1 | Window and door schedule and ironmongery (access control?) | 17/03/2025 |  | Waiting on Dorma
2 | Fencing and gates | 19/03/2025 |  | VOIDED - Plaster and paint - Pricing offset?
3 | Façade cladding/timber work | 24/03/2025 |  | Check on Dickey. Engineer's invoice
4 | Bathroom fittings and mirrors | 24/03/2025 |  | Completed
5 | Electrical, AC, Fire, access control, alarms | 24/03/2025 |  | Electrician to update pricing
6 | Electrical fittings | 24/03/2025 |  | Completed
7 | Plumbing fittings | 24/03/2025 |  | Completed - Water point in hinterveld for Coffee station?
8 | Ceiling layout etc. | 24/03/2025 |  | Completed
9 | Flagpole | 26/03/2025 |  | Client liaised with 3rd party
10 | Appliances, kitchen equipment, TVs etc. | 26/03/2025 |  | Completed
11 | Tile specs (walls and floors), laminated flooring and carpet tile | 26/03/2025 |  | Completed
12 | Signage | 04/04/2025
13 | Joinery details | 04/04/2025 |  | Completed
14 | Glass roof design/details | 04/04/2025 |  | Completed
15 | Structures to cladding | 04/04/2025 |  | SORTED - Engineer to ensure his drawing is updated with ours.
16 | Paint colours and wall paper | 14/04/2025 |  | Dulux Kylie - Has sent the specifications - Need to choose colours
17 | Paving | 21/04/2025
18 | Signage | 07/05/2025
19 | Blinds | 30/05/2025
20 | Landscaping | 30/05/2025